## AB23
Host site |  | ZAPP site related |  | District | Work type | Cluster | Site acces OK | Installation |  | 2G swap/activation |  |  |  | 3G swap/activation |  |  |  | 4G activation |  |  |  | SC | DUG 20 | TCU | BB Type |  | Radio Config | [7 empty] | TCI received | XML files | SWAP SCHEDULE | Swap start hour | E/// NOC responsible |  | On site Team Leader |  | E/// coordinator |  | E/// Project Manager |  | E/// RNO responsible |  | SWAP TIME | Comments Ericsson | Status @ 30.08.2018; 07:00 p.m. | [6 empty] | Status swap @ xx.08.2018; 09:00 p.m.
Site code | Site name | Site code | Site name |  |  |  |  | start | end | Ready | Poposed | planned ERI | actual | Ready | Poposed | planned ERI | actual | Ready | Poposed | planned ERI | actual |  |  |  | 5216 | 5212 | R2219 B1 | R2219 B3 | R2219 B8 | R2217 B3 | R2217 B20 | R2242B1/B3 | RRUS01 B3 | RRUS12 B3 | [6 empty] | SwapTeam | [9 empty] | HW installation | GB - E/// FE - existing | TCU integrated | 2G pre-integrated | 3G pre-integrated | 4G pre-integrated | Observations | 2G integrated | 3G integrated | 4G integrated | Observations
[8 empty] | planned | [30 empty] | Name / Phone |  |  |  | Name / Phone |  | Name / Phone |  | Name / Phone
6 | 6 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 0 | 4 | 4 | 6 | 3 | 6 | 6 | 6 | 6 | 0 | 4 | 0 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 3 | 6 | 0 | 0 | 0 | 0
CJ105 | BAIA_DE_ARIES_ORG |  |  | ALBA | swap2G+swap3G+new4G-800 | AB23b | ? |  |  |  | W22 | w36 |  |  | W22 | w36 |  |  | W22 | w36 |  | StarNet | NA | NA | 1 |  | 2 |  | 2 |  | 2 | [5 empty] | 2018-09-07 | [5 empty] | Cristian Mircea | 0760690452 | Lucian Vilcu |  |  |  |  | acces dificil - ultimul KM se face pe jos sau caruta, tractor |  | na | na |  |  |  | TCI ok. Cheie la Deva
CJ117 | SALCIUA |  |  | ALBA | swap2G+swap3G+new4G-800 | AB23b | 2018-07-04 |  |  |  | W22 | w36 |  |  | W22 | w36 |  |  |  | w36 |  | StarNet | NA | NA | 1 |  | 3 |  | 3 |  | 3 | [5 empty] | 2018-09-07 | [5 empty] | Cristian Mircea | 0760690452 | Lucian Vilcu |  |  |  |  | acces dificil - nu se poate ajunge cu masina la site |  | na | na |  |  |  | TCI ok.Cheie de la Sibiu
CJ409 | ROSIA_MONTANA_RTC |  |  | ALBA | swap2G+swap3G+new4G-800 | AB23a | 2018-06-20 |  |  |  | W22 | w36 |  |  | W22 | w36 |  |  | W22 | w36 |  | StarNet | NA | NA | 1 | 1 | 4 |  | 4 |  | 4 | [5 empty] | 2018-08-30 | 10:00 | Kumar | +918861186441 | Tibi Trif | `0760690498 | Cristian Mircea | 0760690452 | Lucian Vilcu |  |  |  |  | acces dificil | done | na | na | ok | ok | ok
CJ439 | PONOR_RTC |  |  | ALBA | swap2G+swap3G | AB23b | 2018-06-19 |  |  |  | W22 | w36 |  |  | W22 | w36 |  | NA | NA | NA | NA | StarNet | NA | NA | 1 |  |  |  | 3 | [7 empty] | 2018-09-07 | [5 empty] | Cristian Mircea | 0760690452 | Lucian Vilcu |  |  |  |  | acces dificil - 5Km de drum forestier, ingust si in panta |  | na | na |  |  | na | TCI ok
CJ442 | SALCIUA_DRTV |  |  | ALBA | swap2G+swap3G | AB23b | 2018-07-18 |  |  |  | W22 | w36 |  |  | W22 | w36 |  | NA | NA | NA | NA | StarNet | NA | NA | 1 |  | 2 |  | 2 | [7 empty] | 2018-09-07 | [5 empty] | Cristian Mircea | 0760690452 | Lucian Vilcu |  |  |  |  | acces dificil - 13Km drum de pamant |  | na | na |  |  | na | TCI ok
CJ572 | MOGOS_RTC |  |  | ALBA | swap2G+swap3G | AB23a | 2018-06-19 |  |  |  | W22 | w36 |  |  | W22 | w36 |  | NA | NA | NA | NA | StarNet | NA | NA | 1 |  |  |  | 3 | [7 empty] | 2018-08-30 | 13:00 | Ivan | +38268100298 | Tibi Trif | `0760690498 | Cristian Mircea | 0760690452 | Lucian Vilcu |  |  |  |  | acces dificil | done | na | na | ok | ok | na
CJ783 | POSAGA_RTC |  |  | ALBA | swap2G+swap3G+new4G-800 | AB23b | 2018-06-20 |  |  |  | W22 | w36 |  |  | W22 | w36 |  |  |  | w36 |  | StarNet | NA | NA | 1 |  | 2 |  | 3 |  | 3 | [5 empty] | 2018-09-07 | [5 empty] | Cristian Mircea | 0760690452 | Lucian Vilcu |  |  |  |  | acces dificil - pericol animale salbatice |  | na | na |  |  |  | TCI ok.
CJ812 | MAMALIGANI |  |  | ALBA | swap2G+swap3G | AB23a | 2018-07-02 |  |  |  | W22 | w36 |  |  | W22 | w36 |  | NA | NA | NA | NA | StarNet | NA | NA | 1 |  |  |  | 4 | [7 empty] | 2018-08-29 | 17:30 | Kumar | +918861186441 | Tibi Trif | `0760690498 | Cristian Mircea | 0760690452 | Lucian Vilcu |  |  |  |  | acces dificil - 3,5 Km drum de pamant | done | na | na | ok | ok | na
CJ815 | INTREGALDE_RTC |  |  | ALBA | swap2G+swap3G | AB23a | 2018-06-19 |  |  |  | W22 | w36 |  |  | W22 | w36 |  | NA | NA | NA | NA | StarNet | NA | NA | 1 |  |  |  | 3 | [7 empty] | 2018-08-30 | 16:00 | Ivan | +38268100298 | Tibi Trif | `0760690498 | Cristian Mircea | 0760690452 | Lucian Vilcu |  |  |  |  | acces dificil - ultimii 500m drum de pamant | done | na | na | ok | ok | na
CJ821 | SAGACEA |  |  | ALBA | swap2G+swap3G | AB23b | 2018-07-04 |  |  |  | W22 | w36 |  |  | W22 | w36 |  | NA | NA | NA | NA | StarNet | NA | NA | 1 |  |  |  | 3 | [7 empty] | 2018-09-07 | [5 empty] | Cristian Mircea | 0760690452 | Lucian Vilcu |  |  |  |  | acces dificil - drum de pamant |  | na | na |  |  | na | TCI ok.

## RF
Host site
Site code | Site name | Antena | Antena | Antena | Antena | Antena | Antena | Combiner
|  | 80010665V01 | 80010291V02 | LDX-6516DS-VTM | 80010666v01 | DBXLH-6565B-VTM | HWX-6516DS1-VTM | E11F02P72
10 | 10
CJ105 | BAIA_DE_ARIES_ORG | 3 | [5 empty] | 3
CJ117 | SALCIUA |  | 3 |  |  |  |  | 3
CJ409 | ROSIA_MONTANA_RTC |  |  | 3 |  |  |  | 3
CJ439 | PONOR_RTC
CJ442 | SALCIUA_DRTV |  |  |  | 1 | 1
CJ572 | MOGOS_RTC
CJ783 | POSAGA_RTC |  |  | 3 |  |  | 2 | 2
CJ812 | MAMALIGANI
CJ815 | INTREGALDE_RTC
CJ821 | SAGACEA

## SAQ
Host site
Site code | Site name | SAQ
10 | 10 | 0
CJ105 | BAIA_DE_ARIES_ORG
CJ117 | SALCIUA
CJ409 | ROSIA_MONTANA_RTC
CJ439 | PONOR_RTC
CJ442 | SALCIUA_DRTV
CJ572 | MOGOS_RTC
CJ783 | POSAGA_RTC
CJ812 | MAMALIGANI
CJ815 | INTREGALDE_RTC
CJ821 | SAGACEA